## Conference Organizer Timeline
Task | Responsible | Timeframe | Relevant Link
Establish Conference Organizing Committee; contact previous year's Committee/Steering Committee for best practices | General Chair | 36-12 months out
Contact CEE (events@ieee.org) for conference mentor, education, guidance, policies, services, & tools | General Chair | 36-12 months out
Reach out, apply, & obtain sponsorship information from all IEEE &/or non-IEEE OUs. | General Chair | 36-12 months out
Create & finalize scope, topic, or theme. Check for date/scope conflicts with other IEEE/CASS conferences. | General Chair | 36-12 months out | https://www.ieee.org/conferences-events
Engage with local IEEE Section leadership where your conference will be held. How can you partner? | General Chair | 36-12 months out
Select conference date, location, & venue. Tip: avoid holidays, other conferences, and peak season. | General Chair | 36-12 months out
Seek input and approval on registration fees and other key aspects of the conference budget. *Organizers of financially sponsored conferences must offer a registration discount to CASS members of at least $22 USD, to be offered as a separate registration type from IEEE Members. | Finance Chair/Treasurer | 36-12 months out | https://events.ieee.org/planning-basics/event-registration/determining-accepting-registration-fees/
Draft conference budget. | Finance Chair/Treasurer | 36-12 months out | https://events.ieee.org/planning-basics/finance-contracts/budget/
After agreeing with sponsors, submit Conference Application to apply for IEEE sponsorship support & inclusion in IEEE Conference Search. Approve MOU. | General Chair | 36-12 months out
Confirm venue & vendor contracts. Send contracts valuing over US $1,000 to contracts team for review. | Local Arrangements Chair | 36-12 months out
Submit budget to IEEE CEE for review & approval. This will also be collected by the CASS Conference Portfolio Manager (and approved by the CASS VP-Conferences and VP-Finance) upon conference application receipt. | Finance Chair/Treasurer | 36-12 months out
After budget approval, learn audit requirements for documentation throughout the life of the conference. Conferences that do not require an audit by Policy are open to random testing by IEEE Internal Audit. | Finance Chair/Treasurer | 36-12 months out
After budget approval, establish means for filing indirect taxes if applicable, prior to collecting any revenue or making payments | Finance Chair/Treasurer | 36-12 months out
After budget approval, establish Bank Account and submit required documentation to assigned analyst. | Finance Chair/Treasurer | 36-12 months out
Request loan to your conference account after establishing (if applicable) | Finance Chair/Treasurer | 36-12 months out
Complete POBC/COI Form within 30 days of assuming Chair/Treasurer position. Once your event has been approved, the Chair(s) and Treasurer(s) will automatically receive an email requesting that they complete their POBC/COI. | General Chair/Finance Chair/Treasurer | 24-12 months out
Create conference branding & basic website. Share URL with CEE and CASS Portfolio Manager. | General Chair | 18-15 months out | https://events.ieee.org/planning-basics/getting-started/conference-branding-websites/
Determine if VAT management is needed and contact IEEE for details. | Finance Chair/Treasurer | 18-15 months out
Establish paper submission process/deadlines. Include Crosscheck or plagiarism detection tool. | Technical Program Chair | 18-15 months out
Apply for grants for conference support. | General Chair | 18-12 months out
Set up online paper management system | Technical Program Chair | 18-12 months out
Draft a Call for Papers (CFP). Provide to CASS Conference Portfolio Manager for posting on the CASS website. | Technical Program Chair | 18-12 months out
Work with Finance Chair to establish sponsorship targets & development of tiers | Sponsorship/Exhibits Chair | 18-12 months out
Prepare Exhibit Prospectus. Send request for proposal (RFP) to exhibit decorators. | Sponsorship/Exhibits Chair | 18-12 months out
Establish a means of exhibitor & sponsor invoicing & payment tracking | Sponsorship/Exhibits Chair | 18-12 months out
Submit IEEE Conference Publication Form to request approval to submit papers to IEEE Xplore® | Publications Chair | 18-12 months out | https://conferences.ieee.org/application/home?appName=Publication
Register for PDF eXpress (optional). The Conference Organizer requests a PDF eXpress site when completing the IEEE Conference Publication Form. | Publications Chair | 18-12 months out
Develop communications/audience development plan. Incorporate milestones - call for papers promotion, early bird deadlines, and speaker/program announcements. For submitting requests to the CASS marketing team, use this form. | Publicity/Public Relations Chair | 16 months out | https://forms.clickup.com/8482348/f/82vhc-353534/N05UA080OBZ51UCJEZ
Begin outreach to educational institutions, corporations, government, & industry for support & patronage. Ask companies to do press releases for keynotes as they accept. | Publicity/Public Relations Chair | 15 months out
Develop technical program (include underrepresented groups: local, young professionals, women, students) | Technical Program Chair | 15-12 months out
Promote Call for Papers (CFP) & Exhibit Prospectus at current year's conference, if applicable | Publicity/Public Relations Chair | 15-12 months out
Establish Production Services for conference content | Publications Chair | 15-12 months out
Determine registration process/vendor. Include IEEE Event Terms and Conditions & IEEE Privacy Policy. | Registration Chair | 12-9 months out
Work with Finance Chair to develop registration scenarios (early bird, etc.) | Registration Chair | 12-9 months out
Determine conference awards process. | General Chair | 12-9 months out
Create sponsor & exhibit report w/entity name, item purchased, amount paid, method of payment, & date paid | Sponsorship/Exhibits Chair | 12-1 months out
Update website (Call for Papers, Exhibit Prospectus, venue/hotel, key dates, author instructions, & program) | Publicity/Public Relations Chair | 12 months out-launch
Promote conference through your sponsoring OU and local IEEE sections | Publicity/Public Relations Chair | 12 months out-launch
Plan social activities and tour program, if applicable. and add to registration site | Local Arrangements Chair | 9-6 months out
Create GDPR-compliant registration form (& visa process if applicable). Ensure registration service is Payment Card Industry (PCI) compliant. | Registration Chair | 9-6 months out
Establish review committee. Complete paper review process. Notify authors. | Technical Program Chair | 6-4 months out
Finalize technical program. Sign off on final copy or delegate to ensure quality control. | Technical Program Chair | 6-4 months out
Create & publish advanced program. | Technical Program Chair | 6-4 months out
Issue travel grants if applicable. The CASS Conference Portfolio Manager will work with Flagship Chairs on this process. | General Chair/Finance Chair/Treasurer | 6-1 months out
Request that IEEE increase conference credit card limit (if needed). | Finance Chair/Treasurer | 4 months out-launch
Register for eCF for accepted papers 90 days prior to Notification of Acceptance. | Publications Chair | 4 months out-launch
Work with vendor on name badges. Contact CEE to learn about discounts. | Registration Chair | 4 months out-launch
Finalize exhibitors, space assignments & exhibitor bios. | Sponsorship/Exhibits Chair | 4 months out-launch
Work w/vendors/venue to finalize room layout, AV, food & beverage, & signage. Finalize volunteer assignments. AV should include a quote for keynote recording as required by CASS. | Local Arrangements Chair | 4 months out-launch
Create Event Emergency Plan & share with conference committee, volunteers, & vendors on-site | Local Arrangements Chair | 4 months out-launch
Order on-site items: registration materials, final program, proceedings, signage, giveaways, and items to promote next year's conference. Ship to site. | Local Arrangements Chair | 4 months out-launch
Send Proceedings out to conference registrants. | Publications Chair | On-site
Notify CEE of on-site event emergencies (eert@ieee.org) & event conduct concerns (eventconduct@ieee.org) | General Chair | On-site
Hold post‐conference wrap-up meeting. Include next year's committee if possible. | General Chair | On-site
Issue reimbursements for conference travel expenses (if applicable). | Finance Chair/Treasurer | On-site-1 month post
Submit Conference Proceedings/Content to IEEE Xplore per LoA 30 days post conference start date. Submit selected papers to IEEE CAS Journals if the conference benefits from special editions. | Publications Chair | 2 weeks-1 month post
Review & reconfirm hotel meeting space & room block. Monitor attrition cut off dates. | Local Arrangements Chair | 12-9 months out
Ensure that all vendors and volunteers are fulfilling duties. Conduct periodic quality check in. | General Chair | Monthly
Submit pre-conference forecast (including updates to projected attendance based on paper submission numbers, confirmed financial contributions, expenses, etc.). Multiple forecasts are helpful. | Finance Chair/Treasurer | Monthly
Collect & record payments and provide on-site information | Sponsorship/Exhibits Chair | Monthly
Monitor additional revenue & expenses on-site, request daily bills from vendors to review for accuracy, review on-site transactions with forecast numbers daily. Make registrar aware of any additional on-site revenue. | Finance Chair/Treasurer | On-site
Collect tax forms from individuals receiving awards or any non-reimbursable payments | Finance Chair/Treasurer | On-site | https://www.ieee.org/about/related-info
Share Event Conduct & Safety Statement with attendees | Publicity/Public Relations Chair | On-site | https://events.ieee.org/planning-basics/general-guidelines/ieee-event-conduct-and-safety-statement-for-conferences/
Promote next year's conference with collateral, including Save the Date, Call For Papers, & Exhibit Prospectus | Publicity/Public Relations Chair | On-site
Manage on-site registration | Registration Chair | On-site
Arrive at conference location at least one day prior to conference start. Confirm on-site logistics with venue. | Local Arrangements Chair | On-site
Monitor on-site activities & hold meetings with key organizers, vendors, and venue as needed. | Local Arrangements Chair | On-site
Set up for event: registration area, exhibit space, information booth, office area, signage, etc. | Sponsorship/Exhibits Chair | On-site
Establish location, schedule, & staffing sign-up for next year's conference. Renew exhibitors on-site. | Sponsorship/Exhibits Chair | On-site
Send post-event thank you email & attendee survey | Publicity/Public Relations Chair | 1 day - 1 week post
Send keynote speaker recordings to CASS Conference Portfolio Manager for posting on Resource Center and ILN. | General Chair | 1 day-1 month post
Post photos, video content, multimedia & notices of appreciation on the website | Publicity/Public Relations Chair | 1 day-1 month post
Post next year's date and location on the website | Publicity/Public Relations Chair | 1 day-1 month post
Provide conference data to CASS Conference Portfolio Manager in provided data sheet. | General Chair | 1 day-1 month post
Report statistics & lessons learned to OU with copy to CEE | General Chair | 1 month post
Finalize attendee list - attendee name, item purchased, amount paid, payment method, date paid & no shows. Send to IEEE CEE with closing materials. | Registration Chair | 1 month post
Submit post-conference forecast | Finance Chair/Treasurer | 1 month post
Follow-up for any outstanding bills/final invoices | Finance Chair/Treasurer | 1 month post
Review 1099 1042 & make sure it is submitted to your Business Analyst by year end | Finance Chair/Treasurer | 1 month post-year end | https://www.ieee.org/about/volunteers/form-1099-1042-information.html
Ensure that support transfers from IEEE sponsors are submitted to your Business Analyst by year end | Finance Chair/Treasurer | 1 month post-year end
Close bank account, distribute surplus & loan if applicable to financial sponsors (no later than 6 months) | Finance Chair/Treasurer | 1-6 months post | Business analyst will contact organizers with details.
Submit final financial report with Certificate of Accuracy (no later than 12 months after conference) | Finance Chair/Treasurer | 1-12 months post | Business analyst will contact organizers with details.
Prepare & submit all audit material to IEEE auditor or independent auditor (as necessary) | Finance Chair/Treasurer | 1-12 months post