## Slide 1
Universalization in IC Design by CASS (UNIC-CASS)
Meet-up #6 ( Sept 27th, 2023 )
Welcome to : Students
Mentors
CASS Volunteers IC Professionals
Sept 27th, 2023, 09:00am EDT (UTC-4)
Moderators: Sergio Bampi & Jorge Marin
UNIC-CASS Design-to-Tapeout Mentoring

## Slide 2: Meet-up #6 Agenda
9.00-9.05: Welcome & Review Today´s agenda
9:05 : 9:15 Review Tapeout Milestones ( Sergio Bampi) (Federal Univ. UFRGS, Brazil)
9:15-9:30: “Prechecks Reports by each Design Team- A Summary “ Mock tapeout milestone
by Jorge Marin (Univ. F. S. M. , Chile)
9:30-9:45 Q&A by Design Teams and Suggestions by all mentors
09:45: 9:55 Call to Design Reviews by local team Mentor
09:55 –10:15 Q&A
10:15: Adjourn

## Slide 3: UNIC-CASS thanks to: Molly Brackin at Conference Catalysts for her support behind the scenes All previous mentoring sessions are recorded and available at the UNIC-CASS homepage https://ieee-cas.org/universalization-ic-design-cass-unic-cass

## Slide 4
UNIC-CASS Program Overview

## Slide 5: Universalization in IC Design by CASS (UNIC-CASS)
Material available in GitHub ( github.com/unic-cass ), slack channel (https://unic-cass.slack.com/ ), CASS Microlearning (https://ml.ieee-cas.org)
Benefits:
Learn by experience from IC to chip test/bring-up.
Discover using open-source EDA tools and Open PDKs.
Enhance students' professional careers
How it works?
      Learn: Jumpstart your journey from carefully curated materials on CASS MiLe platform
      Design: Hands-on design mentoring by experts in the field,
      Fabricate: Submit designs to CASS-sponsored fabrication runs via Efabless chipIgnite program
      Test: “Bringup” your fabricated chip at selected testing facilities.
What is UNIC-CASS?
A structured end-to-end Integrated Circuit (IC) design-to-test experiential learning program. strategic cooperation with the SSCS serving geographical-complementing locations.
Aim:
To improve the know-how and accessibility to IC Design technologies for enthusiasts and design communities worldwide
https://ieee-cas.org/universalization-ic-design-cass-unic-cass
Notes: What is UNIC-CASS (Aim, Synergy with SSCS, Benefit)
UNIC-CASS Calendar
The program (Education, Mentoring, Chip bringup)
2023 UNIC-CASS submission
Whos’ who in UNIC-CASS

## Slide 6: UNIC-CASS Milestones - 2023
Date | Activity
June 22nd | First Call for Participation
July 28th | Deadline for Students Proposal submission
Aug 17th | WW UNIC-CASS Webinar (world-wide) – Stream from CASS Resource Center
Aug 18th | Announcement : 27 Design teams Selected
Aug 23rd – Oct 30 | Design-to-Tapeout Mentoring sessions Learn from specially curated educational materials
Sept 14th | DESIGN TEAMS: Survey response in a Google Form
Sept 22 | Mock-tapeou t DELIVERED by 16 Design TEAMS
Nov 6, 2023 | Efabless Deadline for Clean & Top-level layout submission
April 2024 | Start Chip test/bring-up

## Slide 7: 2023 UNIC-CASS submissions 68 Team Proposals 16 Countries

## Slide 8: 2023 UNIC-CASS Selected Design Teams @Start line : 27 Teams 11 Countries
Latin America: 14
Far East: 11
Region 8 : 2

## Slide 9
UNIC-CASS Design-to-Tapeout
Meet up organizers
Sergio Bampi
Federal Univ. of Rio Grande do Sul, Brazil
Jorge Marin
Univ. Tecnica Federico Santa Maria, Chile

## Slide 10
Design-to-Tapeout activities schedule I
Activities | Date/ Deadline | Purpose | Your Deliverables (provide info/links on your GitHub) | 
WW Webinar | Aug 17, 2023 | UNIC-CASS Introduction & WW Webinar |  | 
Weekly meet-ups | Aug 23, Aug 30, Sep 6, Sep 13, Sep 20 | Mentoring and Design groups to present progress. Invite short presentations on topics such as Caravel/Caravan, best practices, pitfalls to avoid. Invited talks. eFabless, Digital Flow, Analog Flow , Pitfalls on Schematics, Pitfalls on custom-layout. |  | Kick-off with the selected Design Teams.
1st Design submission [Mock tapeout] | Sept 22 |  | Disclosed on Sept 13 | 1. Merge designs 2. Run local pre-checks
1st Design Review & Feedback | Sept 29 | Done with STUDENTS and their respective LOCAL MENTOR |  | Feedback on the “merge-run pre-check”, Design Progress

## Slide 11
Design-to-Tapeout activities schedule II
Activities | Date/ Deadline | Purpose | Your Deliverables (provide info/links on your GitHub) | We will provide/handle
Weekly meet-ups | Oct 4, Oct 11 | Guide to final submission and solve teams’ issues. | A check-list of to-dos to the Design Teams. Evaluate status of potential “drop-outs”. | 
2nd Design submission | Oct18 |  | TBD | Check all blocks are LVS, DRC clean.
2nd Design Review & Feedback | Oct 22 |  | Maybe a 1-week extension for late bugs detected | Delivery by Design teams of their finished blocks in GDSII.
eFabless pre-check | Nov 3 |  | Deliver 2 Caravelle drop-ins to e-Fabless to check | 
Tape-out | Nov 6 | Finish line! |  | List of “winner teams” included in this Tapeout. List of unfinished Designs to candidate for April, 2024 UNIC-CASS Call

## Slide 12: Design-to-Tapeout mentoring activities
Sept 27th : Session #6
Oct 4th : Session #7
Oct 11th : Session #8
Oct 18th : Session #9
Oct 25th : Session #10

## Slide 13: Call to action : To all DT Mentors: It is time for Design Reviews by each Team - in meeting with the Local Mentor Each team sets up its internal Review Meeting (online or in-person)
Finish Review by Oct 3rd, 2023